## Operating Model
Donor Stewardship Operating Model — FY27
Operating Plan
The Donor stewardship program is organized by donor's tier, fund type, and engagement preferences. This workbook organizes that work into four layers: (a) standing service commitments delivered to every fundholder by tier, (b) tier-specific high-touch stewardship, (c) a calendared overlay of signature events, educational programming, and campaigns, and (d) outreach triggered by community and donor life events. The Gantt tab is the timeline that connects the plan across the fiscal year.
1. Operating Model | This sheet.
2. Service Tiers | WHO & WHAT. Donor segmentation by engagement tier (Tier 1–4) plus the Planned Gift overlay and Professional Advisor track.
3. Standing Cycle | The recurring service touchpoints every fundholder receives by tier.
4. FY27 Ops Plan (Gantt) | WHEN, sequenced. Week-by-week timeline (Jul 2026–Jun 2027) of every stewardship activity, color-coded by touch type.
5. Stewardship Touchpoints | The month-by-month master list, tagged by tier and fund-type filter, that the Gantt sequences.
6. Annual Calendar | Dated overlay of signature events, campaigns, and programming on the standing cycle.
7. Donor Education | Two donor white papers + two site visits per year + Funders Tour
8. Professional Advisors | Parallel CLE and outreach program for attorneys, CPAs, and financial advisors — the referral engine.
9. Responsive Triggers | Non-calendared stewardship triggered by community events, fund anniversaries, and donor life events.

## Service Tiers
Donor Service Tiers
Tier | Qualifying Criteria | Types | Annual Touchpoints | Lead Staff | Service Commitment | Portfolio Max
Philanthropic Advisory (Tier 1) | Fund balance ≥ [PLACEHOLDER]; complex multi-generational giving; private foundation conversions; family philanthropy engagements | Donor-Advised, Designated, Family, Field of Interest, Scholarship (committee-advised) | 8–10 substantive touchpoints; ≥3 face-to-face; annual philanthropic review; biennial strategy session | VP Philanthropy | Personalized philanthropic strategy; next-gen engagement; private-foundation-level services | 30-35 relationships
Major Donor (Tier 2) | [PLACEHOLDER]–[PLACEHOLDER]; cumulative giving ≥ [PLACEHOLDER] over x years; | Major Gift donor, Mid-Tier Annual Fund donor with inclination and capacity | 5–7 touchpoints; ≥2 face-to-face; | VP Philanthropy | Annual check-ins; personal invitation to all donor events | 50 relationships
Engaged Fundholder (Tier 3) | Active DAF with grantmaking in trailing 12 months; established giving pattern; emerging major-donor prospects | Donor-Advised, Designated, Agency, Scholarship | 4–5 touchpoints; ≥1 face-to-face or substantive call; annual fund report meeting | Donor Services Officer | Annual fund report review; responsive grantmaking support; donor education invitations; quarterly statements with narrative summary | 100–125 relationships
Standard Fundholder (Tier 4) | All other active fundholders; agency endowments without large advisor relationships; scholarship donors without committees | All fund types | 3–4 touchpoints; quarterly fund statements; annual report; donor education invitations | Donor Services Officer | Quarterly statements with portal access; annual fund report; eNewsletter; event invitations; responsive grant-question support | Balance of portfolio
Planned Gift Donor (overlay) | Confirmed Legacy Society member; documented bequest, beneficiary designation, CRT, CGA, or other deferred gift | Overlay across all fund types — most are also Tier 1–3 | Overlay: Legacy Society luncheon (May); birthday card; anniversary-of-commitment acknowledgment; insider's-view briefing/whitepaper | Donor Services Officer + VP of Philanthropy | Recognition without solicitation; ongoing connection to mission; aim for annual confirmation that intentions remain current | All confirmed planned gift donors
Professional Advisor (parallel track) | Attorneys, CPAs, financial advisors, wealth managers, trust officers who refer or could refer clients to Foundation | N/A — referral source | 3–4 touchpoints/year; CLE events; bar / EPC presentations; thought-leadership content; year-end tax planning resource | VP Philanthropy | CLE programming; technical responsiveness within 24 hours; client meeting support; third-party investment manager program access | Active referral roster of 40–60 advisors
Notes on tier design:
• Tier 1: high-touch service for donors who want philanthropic strategy, next-generation engagement, and private-foundation-level support.
• Planned Gift and Professional Advisor are overlays / parallel tracks, not exclusive tiers — a donor can be Tier 2 and a Legacy Society member simultaneously.
• Tier movement will be reviewed twice annually (January and July). Donors do not need to know their tier; tiers govern internal resource allocation, not donor-facing recognition.

## Standing Cycle
Standing Touchpoint Cycle
Touchpoint | Cadence | Channel | Tier 1 | Tier 2 | Tier 3 | Tier 4 | Owner
New Fund Welcome Packet | Within 5 business days of fund opening | Mail + email + portal | ✓ | ✓ | ✓ | ✓ | Donor Services Manager
New Fund Orientation Meeting | Within 30 days of fund opening | In-person or video | ✓ (60 min) | ✓ (60 min) | ✓ (60 min) | ✓ (30 min) | VP of Philanthropy
Quarterly Fund Statement | Q1 Oct 15 · Q2 Jan 15 · Q3 Apr 15 · Q4 Jul 15 | Email + portal | ✓ + narrative | ✓ + narrative | ✓ + narrative | ✓ | Donor Services Officer
Annual Philanthropic Review | Within 60 days of fund anniversary | In-person preferred | ✓ (required) | ✓ (required) | ✓ (offered) | — | VP of Philanthropy
Annual Fund Report | End of FY (July–August). Combine with Q4 Fund Statement | PDF + portal + cover letter | ✓ + personal delivery | ✓ + personal delivery | ✓ | ✓ | VP of Philanthropy + Donor Services Officer
Portal Access & Training | At fund opening + on request | Self-service + tutorial | ✓ | ✓ | ✓ | ✓ | Donor Services Manager
eNewsletter | Monthly | Email | ✓ | ✓ | ✓ | ✓ | Communications
Annual Report (printed) | October | Mail + digital | ✓ + handwritten note | ✓ + handwritten note | ✓ + handwritten note | ✓ | Communications + President
Fund Anniversary Acknowledgment | On fund anniversary date | Handwritten card or call | ✓ (call) | ✓ (card) | ✓ (card) | — | Donor Services Officer + Donor Services Manager
Grant Confirmation | Within 2 business days of grant approval | Email + portal | ✓ | ✓ | ✓ | ✓ | Donor Services Officer
Year-End Tax Statement | January 31 | Mail + portal | ✓ | ✓ | ✓ | ✓ | Donor Services Manager
• ✓ indicates the touchpoint is delivered to all donors in that tier as a baseline service commitment.
• Parenthetical detail (e.g., '60 min', 'handwritten note') specifies the differentiated execution for that tier.
• '—' indicates the touchpoint is not part of the standing commitment for that tier (donors may opt in by request).
• Quarterly statement dates align with the Foundation's fiscal year (July–June). Q1 reflects activity through September 30, etc.

## FY27 Ops Plan (Gantt)
Donor Services Operations Plan — FY 2027
July 2026 – June 2027 · color-coded by touch type · dark = % complete, light = remaining
[8 empty] | 2026 | [25 empty] | 2027
|  | LEAD STAFF | PLANNED START | DURATION (wks) | ACTUAL START | ACTUAL DURATION | % COMPLETE | Jul |  |  |  |  | Aug |  |  |  | Sep |  |  |  | Oct |  |  |  |  | Nov |  |  |  | Dec |  |  |  | Jan |  |  |  |  | Feb |  |  |  | Mar |  |  |  | Apr |  |  |  | May |  |  |  |  | Jun
[8 empty] | 1 | 2 | 3 | 4 | 5 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 5 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 5 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 5 | 1 | 2 | 3 | 4
CALENDAR DEVELOPMENT & TEAM ALIGNMENT
| Finalize FY27 stewardship calendar; confirm with leadership and board | VP of Philanthropy | Jul | 4 |  |  | 60% | bar: Jul 1 to Jul 4
| Confirm Tier 1–4 lead staff | DS Depart | Jul | 4 |  |  | 50% | bar: Jul 1 to Jul 4
| Capacity model — input FTE, tier numbers, touch counts | VP of Philanthropy | Jul | 4 |  |  | 75% | bar: Jul 1 to Jul 4
| Review — tiers, standing service, templates, calendar | DS Depart | Aug | 4 |  |  | 25% | bar: Aug 1 to Aug 4
| Quarterly plan review (Q1–Q4) — compare plan against actuals | DS Depart | Oct | 40 | bar: Oct 1 to Jun 4
STANDING SERVICE COMMITMENTS (ANCHOR)
| Q1 FY27 fund statements (Oct 15) | Donor Services Manager. + Donor Services Officer | Aug | 3 | bar: Oct 1 to Oct 3
| Q2 FY27 fund statements (Aug 15) | Donor Services Manager. + Donor Services Officer | Aug | 3 | bar: Jan 2 to Jan 4
| Q3 FY27 fund statements (April 15) | Donor Services Manager. + Donor Services Officer | Aug | 3 | bar: Apr 2 to Apr 4
| Q4 FY27 fund statements (July 15) | Donor Services Manager. + Donor Services Officer | Aug | 3 | bar: Jul 1 to Jul 3
| Annual fund reports (FY26) — drafting & personalized cover letters | Donor Services Manager. | Feb | 4 |  |  | 10% | bar: Feb 1 to Feb 4
| Annual fund reports (FY26) — mailed | Donor Services Manager. + VP of Philanthropy | Nov | 2 | bar: Nov 1 to Nov 2
| Annual Report (printed) — content, design, production | Communications | Aug | 9 |  |  | 10% | bar: Aug 1 to Oct 1
| Annual Report (printed) — mailed to all fundholders + community | Communications | Nov | 2 | bar: Nov 1 to Nov 2
| Year-end tax statements (Jan 31) | Donor Services Officer/Donor Services Manager. | Jan | 2 | bar: Jan 1 to Jan 2
| New fund welcome packets & 30-day orientations (rolling) | Donor Services Manager./VP of Philanthropy | Jul | 48 |  |  | 10%
TIER 1 — PHILANTHROPIC DSISORY (30–35)
| Fall strategy sessions — schedule by end October | VP of Philanthropy | Aug | 10 | bar: Aug 1 to Oct 2
| Mid-Year Review/Check in calls | VP of Philanthropy | Jul | 48 |  |  | 10%
| Event invitations; Personalization | Donor Services Officer
| Spring strategy sessions — schedule by end May | VP of Philanthropy | Mar | 10 | bar: Mar 1 to May 2
| Handwritten notes — birthday, anniversary, annual report (rolling) | Donor Services Manager | Jul | 48 |  |  | 10%
TIER 2 — MAJOR DONOR (50)
| Annual philanthropic check-in (interests and opportunities) | VP of Philanthropy | Sep | 32
| Event invitations; Personalization | Donor Services Officer
| Mid-year check-in calls | Donor Services Officer | Jan | 6 | bar: Jan 1 to Feb 1
TIER 3 — ENGAGED FUNDHOLDER (100–125)
| Annual fund report meetings — ≥1 F2F or substantive call (rolling) | Donor Services Officer | Oct | 28 | bar: Oct 1 to Apr 2
| Q2 FY27 fund statements with narrative summary (overlay) | Donor Services Officer | Aug | 40 | bar: Aug 1 to May 2
| Event invitations; Personalization | Donor Services Officer
| Responsive grantmaking support (rolling) | VP of Philanthropy | Jul | 48 |  |  | 5%
TIER 4 — STANDARD FUNDHOLDER (balance of portfolio)
| Q2 FY27 fund statements + portal access (overlay) | Donor Services Manager. | Oct | 40 | bar: Oct 1 to Jun 4
| Event invitations | Donor Services Manager. | Jul | 48 |  |  | 10%
| Responsive grantmaking support (rolling) | VP of Philanthropy | Jul | 48 |  |  | 5%
PLANNED GIFT / LEGACY SOCIETY (overlay)
| Insider's-view briefings (summer & year-end) | Donor Services Officer | Aug | 1 | bar: Aug 1
| Legacy Society year-end note — no solicitation (Dec) | Donor Services Officer | Dec | 2 | bar: Dec 1 to Dec 2
| Anniversary-of-commitment & birthday acknowledgments (rolling) | Donor Services Officer | Jul | 48 |  |  | 5%
FUND-TYPE STEWARDSHIP MODULES (layered on tiers)
| Scholarship — applicant-pool update notes (Feb) | VP of NP Services | Feb | 4 | bar: Feb 1 to Feb 4
| Scholarship — awards announcement & recognition (May) | VP of NP Services | May | 2 | bar: May 1 to May 2
| Scholarship — fall scholar updates w/ photo card (Sep) | VP of NP Services | Sep | 2 | bar: Sep 1 to Sep 2
| FOI — impact summary | Donor Services Officer | Sep | 3 | bar: Sep 1 to Sep 3
| FOI — mid-year impact note tied to fund purpose | Donor Services Officer | Apr | 2 | bar: Apr 1 to Apr 2
| Agency endowment — planning-season calls (Oct, FY28 alignment) | VP of Philanthropy | Oct | 4 | bar: Oct 1 to Oct 4
| Agency endowment — annual review with each board liaison | VP of Philanthropy | Jan | 12 | bar: Jan 1 to Mar 3
SIGNATURE & SPECIAL EVENTS
| Golf Outing — planning & sponsor cultivation | Donor Services Manager | Jul | 14 |  |  | 10% | bar: Jul 1 to Oct 1
| Golf Outing — event (mid-October) | Donor Services Manager | Oct | 1 | bar: Oct 1
| Annual Meeting — planning & invitations | VP of Philanthropy + Donor Services Manager | Jan | 9 | bar: Jan 1 to Feb 4
| Annual Meeting — event week (mid-March) | VP of Philanthropy + Donor Services Manager | Mar | 1 | bar: Mar 1
| Annual Meeting — follow-up calls (Tier 1 attendees) | President + VP of Philanthropy + Donor Services Officer | Mar | 2 | bar: Mar 1 to Mar 2
| Donor House Party #1 | Donor Services Officer + Donor Services Manager
| Donor House Party #2 | Donor Services Officer + Donor Services Manager
| Donor House Party #3 | Donor Services Officer + Donor Services Manager
| Pre/post-event reminder/thank you/follow up (5 days before/after, rolling) | Donor Services Officer | Sep | 36 |  |  | 5% | bar: Sep 1 to May 2
Donor Education Program (Housing? Food Security?)
DONOR EDUCATION SERIES & SITE VISITS
| White Paper— Donor Education Program Companion (early Aug) | Donor Services Officer | June | 1 | bar: Jul 4 to Aug 2
| Site Visit #1 — Fall Grantee, Tier 1–2 (mid Sep) | VP of Philanthropy | Sep | 1 | bar: Sep 1
| Site Visit #2 — Spring Grantee, Tier 1–2 (mid Apr) | VP of Philanthropy | Apr | 1 | bar: Apr 1
| White Paper — Donor Education Program Companion (late Feb/March) | Donor Services Officer | Apr | 1 | bar: Apr 1
PROFESSIONAL DSISOR PROGRAM
| Face-to-face PA meetings — rolling cadence (target 60/yr) | VP of Philanthropy | Jul | 48 |  |  | 10%
| Summer outreach round — 1:1 calls & coffees (Aug) | VP of Philanthropy | Aug | 4 | bar: Aug 1 to Aug 4
| Year-End Tax Planning Resource distribution (mid Nov) | VP of Philanthropy + Communications | Nov | 2 | bar: Nov 1 to Nov 2
| Estate Planning Council presentation [PLACEHOLDER date] | VP of Philanthropy | Mar | 2 | bar: Mar 1 to Mar 2
| Bar Association presentation [PLACEHOLDER date] | VP of Philanthropy | Apr | 2 | bar: Apr 1 to Apr 2
| CLE #1 — Investment Breakfast - Economic Growth in Your County | VP of Philanthropy | Oct | 1 | bar: Oct 1
| CLE #2 — Complex Assets & Business Succession w/Estate Planning Council | VP of Philanthropy + outside speaker | May | 1 | bar: May 1
| CLE #3 — Planned Giving Vehicles (TBD) | VP of Philanthropy + outside speaker | Feb | 1 | bar: Feb 1
| Quarterly PA eNewsletter | Communications | Sep | 40 | bar: Sep 1 to Jun 1
ANNUAL FUND CAMPAIGN
| Strategy & list segmentation (incl. lapsed-donor track) | VP of Philanthropy | Aug | 4 | bar: Aug 1 to Aug 4
| Mailing design & copy development | Communications | Sep | 4 | bar: Sep 1 to Sep 4
| Annual fund mailing — print & mail (early Nov); lapsed track | Donor Services Manager | Nov | 2 | bar: Nov 1 to Nov 2
| Email follow-up series — November & December | Communications | Nov | 8 | bar: Nov 1 to Dec 4
| Major-donor personal asks — Tier 1–2 (calls/visits) | VP of Philanthropy+President+Donor Services Officer | Nov | 8 | bar: Nov 1 to Dec 4
GIVING DAY CAMPAIGN
| Planning (late July/August) | DS +NP Services + Communications | July | 4 | bar: Jul 1 to Jul 4
| Sponsor cultivation | DS +President | Oct | 16 | bar: Oct 1 to Jan 3
| Nonprofit partner recruitment | DS +NP Services | Oct | 16 | bar: Oct 1 to Jan 3
| Platform, training | NP Services | Jan | 16 | bar: Jan 1 to Apr 3
| PR build | DS +NP Services + Communications | April | 5 | bar: Apr 1 to May 1
| Pre-event mobilization — Tier 1–2 asks & DAF outreach | VP of Philanthropy + Donor Services Officer | Apr | 4 | bar: Apr 1 to Apr 4
| Community celebrations (early May) | DS +NP Services + Communications | May | 1 | bar: May 1
| Post-event donor and NP stewardship, debrief & reporting | VP of Philanthropy + Donor Services Officer + NP services | May | 8 | bar: May 1 to Jun 3
BROAD MESSAGING & MARKETING CONTENT DEVELOPMENT
| Monthly eNewsletter — all tiers + Professional Advisors | Communications + DS Team | Jul | 48 |  |  | 10%
| Mid-year community update (July) — what changed, what we learned | Communications | Jul | 2 |  |  | 100% | bar: Jul 1 to Jul 2
| New Year message / year-ahead orientation (Jan) | Communications | Jan | 2 | bar: Jan 1 to Jan 2
| Local story sourcing & consent process (rolling) | Communications | Jul | 48 |  |  | 10%
| New Fund welcome packets | VP of Philanthropy
| Guide to Effective Philanthropy | VP of Philanthropy
| PA Toolkit | VP of Philanthropy
CAPACITY & OPERATIONS
| Donor Prospecting + Stewardship Meetings + Tier Assignments | Donor Services Officer | Jun | 48
| Mid-year tier review (Jan) — assignments, tier movement | Donor Services Officer | Jan | 2 | bar: Jan 1 to Jan 2
| Lapsed-donor (18-mo) & dormancy review (Jan, Jul) | Donor Services Manager. | Jan | 2 | bar: Jan 1 to Jan 2
| CRM clean-up — tier tags, successor DSisors, dormant funds | Donor Services Manager. | Jul | 8 |  |  | 40% | bar: Jul 1 to Aug 3
| Annual donor survey — design, send (May), analyze | Donor Services Officer | May | 8 | bar: May 1 to Jun 3
| FY27 wrap-up & stewardship effectiveness review (Jun) | Donor Services Officer | Jun | 4 | bar: Jun 1 to Jun 4
| FY28 calendar drafting (start May for July rollout) | VP of Philanthropy | May | 8 | bar: May 1 to Jun 3
LEGEND — TOUCH TYPES
| Anchor | Required, foundation-wide. Statements, annual & fund reports, tax statements, welcome packets.
| High touch | Personal, 1:1. Strategy sessions, reviews, calls, hand-signed notes, site visits.
| Segment | Tailored to a tier or fund type. Education events, briefings, signature events, curated notes.
| Broadcast | Mass communication. Monthly eNewsletter, annual report mailing, foundation-wide messages.
| Campaign | Time-bound fundraising. Annual fund mailing, Delco Gives.

## Annual Calendar & Touchpoints
FY27 Annual Calendar & Stewardship Touchpoints
Month | Wk | Tier(s) | Fund-Type Filter | Event / Touchpoint | Touch Type | Category | Template | Owner | Audience | Notes / Prep | Status
JULY | W1 | All | — | FY27 launch: confirm tier assignments; lock caseloads; capacity model review | ANCHOR | Internal milestone | — | VP of Philanthropy | All staff | Confirm tier assignments; lock annual calendar; portfolio rebalance review
JULY | W1 | Agency | Agency endowment | Fiscal year-end personal call with each agency endowment partner | HIGH TOUCH | — | T-13 | Donor Services Officer | — | —
JULY | W2 | Tier 4 | Agency | Q4 FY26 fund statements (Jul 15) distributed with FY wrap narrative for Tier 1–3 | ANCHOR | Standing — overlay note | T-01 | Finance + DS | All fundholders | Pair with FY26 wrap narrative for Tier 1–3
JULY | W2 | Tier 1–2 | — | Annual fund reports (FY26) drafted; personalized cover letters | ANCHOR | Production | — | Donor Services Manager. | Internal | Personalize cover letters for Tier 1–2; design refresh review
JULY | W3 | All | — | Mid-year community update — what changed, what we learned, what's ahead | BROADCAST | — | — | Communications | — | —
JULY | W4 | Tier 1–2 | — | Dormancy / lapsed-donor (18-mo) review — identify donors off-pattern | ANCHOR | — | — | Donor Services Officer | — | —
JULY | W4 | All | — | July eNewsletter — mid-year update | BROADCAST | — | — | Communications | — | —
AUGUST | W1 | Tier 1–2 | — | Annual fund reports (FY26) mailed; Tier 1–2 hand-delivered or call within 10 days | ANCHOR | Stewardship report | — | Donor Services Manager. + VP of Philanthropy | All fundholders | Tier 1–2 hand-delivered or accompanied by personal call within 10 days
AUGUST | W2 | Tier 1 | — | Tier 1 fall strategy session scheduling — confirm fall calendars | HIGH TOUCH | Outreach | T-02 | VP of Philanthropy | Tier 1 (~30–40) | Confirm fall meeting calendars; target completion by end of October
AUGUST | W3 | Legacy | Planned gift | Insider's-view summer briefing for Legacy Society | HIGH TOUCH | — | T-08 | Donor Services Officer | — | —
AUGUST | W2 | All + advisors | — | White Paper #1 — Summer Briefing [PLACEHOLDER topic] | SEGMENT | White paper | — | VP of Philanthropy + program officer | All Tiers + advisors | Topic: [PLACEHOLDER — Your County human services landscape]
AUGUST | W4 | PA track | Advisor | Summer advisor outreach — 1:1 calls & coffees; surface fall client planning | HIGH TOUCH | Advisor program | — | VP of Philanthropy | PA roster (~50) | Personalized check-ins; surface client planning conversations for fall
AUGUST | W4 | All | — | Annual Report production begins; annual fund strategy & lapsed segmentation | ANCHOR | — | — | Communications + VP of Philanthropy | — | —
SEPTEMBER | W1 | Tier 1–3 | FOI | FOI impact summaries — first of two (Sep) | SEGMENT | — | — | VP of Philanthropy | — | —
SEPTEMBER | W2 | Tier 4 | Scholarship | Fall scholar update with photo card — "Your scholar started classes this week" | SEGMENT | — | T-12 | Donor Services Officer | — | —
SEPTEMBER | W3 | Tier 1–2 | — | Site Visit #1 — fall grantee aligned with Tier 1 interests (~20 attending) | HIGH TOUCH | Site visit | — | VP of Philanthropy + program officer | Tier 1–2 (~20) | Selected grantee with strong donor-interest fit
SEPTEMBER | W4 | All | — | Annual fund mailing — design, copywriting, list pull | BROADCAST | — | — | Communications | — | —
SEPTEMBER | W4 | All | — | Annual Report production locks | ANCHOR | Production | — | Communications + VP of Philanthropy | Marketing | Donor stories and grant impact confirmed; design final review
OCTOBER | W1 | All + community | — | Annual Report mailed; handwritten notes for Tier 1–2 | ANCHOR | Stewardship report | — | Communications + VP of Philanthropy | All fundholders + community | Handwritten notes for Tier 1–2; advisor mailing list refresh
OCTOBER | W2 | All + advisors | — | Golf Outing — sponsor cultivation; new prospect introductions | SEGMENT | Signature event | — | Donor Services Manager | All Tiers + advisors | Existing annual event; sponsor cultivation; new prospect introductions
OCTOBER | W2 | Tier 4 | — | Q1 FY27 fund statements (Oct 15); portal usage reminder; Tier 1–3 narrative summary | ANCHOR | Standing — overlay note | T-01 | Finance + DS | All fundholders | First statement of new fiscal year; portal usage reminder
OCTOBER | W2 | Tier 1 | — | Tier 1 fall strategy sessions — target completion by end October | HIGH TOUCH | — | T-02 | VP of Philanthropy | — | —
OCTOBER | W3 | PA track | Advisor | Professional Advisor CLE #1 — year-end charitable planning (1.0 credit) | SEGMENT | Advisor program | — | VP of Philanthropy + outside speaker | PA roster + guests | Year-end charitable planning; secure 1.0 CLE credit; partner with [PLACEHOLDER bar association]
OCTOBER | W4 | Agency | Agency endowment | Planning-season agency calls — FY28 budget alignment | HIGH TOUCH | — | T-13 | Donor Services Officer | — | —
NOVEMBER | W1 | All + lapsed | — | Annual fund mailing — print & mail; distinct lapsed-donor track | CAMPAIGN | Fundraising appeal | — | Communications + VP of Philanthropy | All fundholders + lapsed | Distinct lapsed-donor track per established practice
NOVEMBER | W2 | PA track | Advisor | Year-End Tax Planning Resource distributed to full advisor list (~150) | BROADCAST | — | — | VP of Philanthropy + Communications | — | —
NOVEMBER | W2 | Tier 1–2 | — | Annual fund: major-donor personal asks (Tier 1–2) | HIGH TOUCH | — | — | VP of Philanthropy | — | —
NOVEMBER | W2 | All | — | Year-end giving readiness check | ANCHOR | Internal milestone | — | VP of Philanthropy + finance | Staff | Confirm gift-processing capacity; appreciated-stock instructions posted
NOVEMBER | W3 | Tier 4 | Scholarship | Thanksgiving note to scholarship families with photo card | SEGMENT | — | T-12 | Donor Services Officer | — | —
NOVEMBER | W3 | Legacy | Planned gift | Insider's-view year-end briefing for Legacy Society | HIGH TOUCH | — | T-08 | Donor Services Officer | — | —
NOVEMBER | W4 | All | — | Thanksgiving acknowledgment from president — no solicitation | BROADCAST | Touchpoint | — | Communications | All fundholders | Brief gratitude message; no solicitation; from president
DECEMBER | W1 | Tier 1–2 | — | Year-end fund reports for Tier 1–2 — calendar-year giving summary | ANCHOR | Stewardship report | — | Donor Services Manager. + VP of Philanthropy | Tier 1–2 | Calendar-year giving summary; tax planning context; precedes Dec 31
DECEMBER | W1 | Tier 2 | — | Year-end giving deadline calls begin — direct, human, through Dec 31 | HIGH TOUCH | — | T-07 | Donor Services Officer | — | —
DECEMBER | W4 | Legacy | Planned gift | Legacy Society year-end note — acknowledgment without solicitation | HIGH TOUCH | Planned gift stewardship | — | VP of Philanthropy + planned giving | Legacy Society | Acknowledgment without solicitation; brief impact note
JANUARY | W1 | All | — | New Year message / year-ahead orientation | BROADCAST | — | — | Communications | — | —
JANUARY | W2 | Tier 4 | Scholarship | "Reading their applications now" note to scholarship families | SEGMENT | — | T-12 | Donor Services Officer | — | —
JANUARY | W2 | Tier 4 | — | Q2 FY27 fund statements (Jan 15); Tier 1–3 narrative summary | ANCHOR | Standing — overlay note | T-01 | Finance + DS | All fundholders | First statement after calendar year-end
JANUARY | W2 | Tier 2 | — | Tier 2 mid-year check-in calls begin | HIGH TOUCH | — | T-03 | Donor Services Officer | — | —
JANUARY | W3 | Agency | Agency endowment | Annual review with each agency board liaison begins | HIGH TOUCH | — | T-13 | Donor Services Officer | — | —
JANUARY | W3 | All | — | Year-end tax statements (Jan 31) | ANCHOR | Standing — overlay note | — | Finance | All donors of record | Deadline-driven; portal availability confirmed
JANUARY | W3 | All | — | Mid-year tier review — portfolio assignments; tier movement; confirm caseloads | ANCHOR | Internal milestone | — | VP of Philanthropy | Staff | Review portfolio assignments; identify tier movement; confirm caseloads
JANUARY | W4 | All + community | — | Giving Day planning launch — Jan–May ramp begins | CAMPAIGN | Campaign prep | — | VP of Philanthropy + Communications | Staff + board | Begin January–May ramp per established practice
FEBRUARY | W1 | PA track | Advisor | Professional Advisor CLE #2 — planned giving vehicles (CGA, CRT, beneficiary) | SEGMENT | Advisor program | — | VP of Philanthropy + outside speaker | PA roster + guests | Planned giving vehicles; CGA, CRT, beneficiary designations
FEBRUARY | W2 | Tier 4 | Scholarship | Scholarship interview-season update; introduce volunteer reviewers | SEGMENT | — | T-12 | Donor Services Officer | — | —
FEBRUARY | W3 | Tier 1 | — | Annual Meeting preparation — Tier 1 personal invitations | SEGMENT | Event prep | — | VP of Philanthropy + Inv. chair | Staff + investment committee | Speaker confirmed; invite list finalized; Tier 1 personal invitations
FEBRUARY | W4 | Legacy | Planned gift | Legacy Society luncheon planning underway (for May event) | HIGH TOUCH | — | — | VP of Philanthropy + planned giving | — | —
FEBRUARY | W4 | All + advisors | — | White Paper #2 — Winter Strategy / Annual Meeting companion [PLACEHOLDER topic] | SEGMENT | White paper | — | VP of Philanthropy + program officer | All Tiers + advisors | Topic: [PLACEHOLDER — issue tied to community priority; pairs with Annual Meeting]
MARCH | W2 | Tier 1–2 + advisors | — | Annual Meeting — annual flagship investment update (mid-March) | SEGMENT | Signature event | — | VP of Philanthropy + Inv. chair | Tier 1–2 + advisors | Annual flagship investment update; high Tier 1 attendance expected
MARCH | W3 | Tier 1 | — | Annual Meeting follow-up calls (Tier 1 attendees) | HIGH TOUCH | — | — | VP of Philanthropy | — | —
MARCH | W3 | Tier 1–3 | Designated/FOI | FOI impact summaries — second of two (Mar) | SEGMENT | — | — | VP of Philanthropy | — | —
MARCH | W4 | Tier 1 | — | Tier 1 spring strategy session window opens — complete by end May | HIGH TOUCH | Cultivation | T-02 | VP of Philanthropy | Tier 1 (~30–40) | Six-month follow-up to fall sessions; target completion by end of May
MARCH | W4 | PA track | Advisor | Estate Planning Council presentation [PLACEHOLDER date] | SEGMENT | — | — | VP of Philanthropy | — | —
APRIL | W1 | PA track | Advisor | Bar Association presentation [PLACEHOLDER date] | SEGMENT | — | — | VP of Philanthropy | — | —
APRIL | W2 | Tier 4 | — | Q3 FY27 fund statements (Apr 15); pair with Giving Day momentum update | ANCHOR | Standing — overlay note | T-01 | Finance + DS | All fundholders | Pair with Giving Day momentum update
APRIL | W2 | Tier 1–3 | Designated/FOI | Mid-year impact note tied to fund's stated purpose | SEGMENT | — | — | Donor Services Officer | — | —
APRIL | W2 | Tier 1–2 | — | Site Visit #2 — spring grantee, cross-sector counterpoint to fall (~20) | HIGH TOUCH | Site visit | — | VP of Philanthropy + program officer | Tier 1–2 (~20) | Spring grantee visit; second of two annual site visits
APRIL | W3 | All + community | — | Giving Day final push (per Jan–May ramp) | CAMPAIGN | Campaign | — | VP of Philanthropy + Communications | All Tiers + community | Per established January–May ramp
APRIL | W3 | Tier 1–2 | — | Giving Day pre-event mobilization — Tier 1–2 personal asks; advisor outreach | HIGH TOUCH | — | — | VP of Philanthropy | — | —
MAY | W1 | Community-wide | — | Giving Day — community giving day | CAMPAIGN | Signature event | — | VP of Philanthropy + Communications | Community-wide | Annual flagship; donor and advisor mobilization
MAY | W2 | Tier 1–2 | — | Tier 1 spring strategy sessions continue — final meetings | HIGH TOUCH | — | T-02 | VP of Philanthropy | — | —
MAY | W2 | Legacy + prospects | Planned gift | Legacy Society annual luncheon — insider's-view briefing; no solicitation | SEGMENT | Planned gift stewardship | — | VP of Philanthropy + planned giving | Legacy Society + prospects | Insider's-view program briefing; recognition without solicitation
MAY | W3 | Tier 4 | Scholarship | Scholarship awards announced — invite families to recognition event | SEGMENT | — | T-12 | Donor Services Officer | — | —
MAY | W3 | All | — | Annual donor survey — design & send (results in June) | ANCHOR | — | — | VP of Philanthropy | — | —
MAY | W4 | PA track | Advisor | Professional Advisor CLE #3 — complex assets, business succession, S-corp gifts | SEGMENT | Advisor program | — | VP of Philanthropy + outside speaker | PA roster + guests | Complex assets, business succession, S-corp gifts
MAY | W4 | All | — | Spring eNewsletter — featured grants, donor stories, what's ahead | BROADCAST | — | — | Communications | — | —
JUNE | W1 | All | — | FY27 wrap-up & stewardship effectiveness review; metrics review | ANCHOR | Internal milestone | — | VP of Philanthropy | Staff + board committee | Year-end stewardship effectiveness review; see Capacity / metrics
JUNE | W2 | Tier 1 | — | Tier 1 summer touch-base — confirm fall meeting interest | HIGH TOUCH | Cultivation | — | VP of Philanthropy | Tier 1 (~30–40) | Brief check-in; surface summer travel; confirm fall meeting interest
JUNE | W2 | PA track | Advisor | Summer recap & FY28 calendar preview; thank advisors for referrals | HIGH TOUCH | — | — | VP of Philanthropy | — | —
JUNE | W4 | All | — | FY28 planning launch — tier reassignments; FY28 calendar drafted; carryover items | ANCHOR | Internal milestone | — | VP of Philanthropy | Staff | Tier reassignments confirmed; FY28 calendar drafted; carryover items identified

## Donor Education
Donor White Papers & Site Visits
Design principles
• Two donor white papers per year, paired with two site visits — four substantive content moments annually.
• Each white paper draws on informed opinion-makers (sector leaders, researchers, practitioners) rather than Foundation staff presentations. [PLACEHOLDER — author / contributor model]
• Site visits are reserved for Tier 1–2 with a seating cap of ~20 to preserve depth of engagement.
• Topics chosen for substantive relevance to community priorities, not for entertainment value.
• Each white paper is distributed with a one-page executive summary. [PLACEHOLDER — distribution channel and timing]
• Site-visit recap with grantee follow-up opportunities distributed within 5 business days after.
Event | FY27 Date | Format | Audience | Speaker / Host | Topic Anchor | Capacity
White Paper #1 — Summer Briefing | Early Aug 2026 | White paper + exec summary | All Tiers + advisors | External: sector researcher / practitioner [PLACEHOLDER] | [PLACEHOLDER — Your County human services landscape] | n/a
Site Visit #1 — Fall Grantee | Mid Sept 2026 | On-site, 2 hours | Tier 1–2 | Grantee executive + program staff + VP of Philanthropy | Grantee aligned with Tier 1 interests; transportation provided | ~20
White Paper #2 — Winter Strategy / Annual Meeting Companion | Late Feb 2027 | White paper + exec summary | All Tiers + advisors | External + Foundation leadership [PLACEHOLDER] | [PLACEHOLDER — issue tied to community priority; pairs with Annual Meeting] | n/a
Site Visit #2 — Spring Grantee | Mid April 2027 | On-site, 2 hours | Tier 1–2 | Grantee executive + program staff + VP of Philanthropy | Second grantee; cross-sector counterpoint to fall visit | ~20

## Professional Advisors
Professional Advisor Program
Program structure
Three pillars: (1) substantive CLE programming three times per year delivering professional-development value, (2) responsive technical support on individual client matters, and (3) thought-leadership presence at bar association, estate planning council, and financial planning association meetings.
Touchpoint | FY27 Timing | Format | Target Audience | Outcome | Lead
Summer outreach round | August 2026 | 1:1 calls & coffees | Active roster (~50) | Surface fall client planning; identify Q4 prospects | VP of Philanthropy
CLE #1 — Year-End Planning | Late Oct 2026 | Breakfast CLE, 1.0 credit | PA roster + prospects (~75) | Position Foundation for Q4 referrals; refresh giving-vehicle knowledge | VP of Philanthropy + outside speaker
Year-End Tax Planning Resource | Mid Nov 2026 | Email + mailed packet | Full advisor list (~150) | Practical client tools; Foundation top-of-mind for Dec 31 | VP of Philanthropy + Marketing
December technical hotline | December 2026 | On-call response | All advisors | 24-hour response on stock gifts, complex assets, fund creation | VP of Philanthropy + finance
CLE #2 — Planned Giving Vehicles | Early Feb 2027 | Breakfast CLE, 1.0 credit | PA roster + prospects (~75) | Deepen CGA/CRT/beneficiary fluency; surface planned-gift prospects | VP of Philanthropy + outside speaker
Estate Planning Council presentation | Spring 2027 [PLACEHOLDER date] | Council meeting slot | EPC members | Reach advisors not yet in roster; thought-leadership presence | VP of Philanthropy
Bar Association presentation | Spring 2027 [PLACEHOLDER date] | Bar event slot | Delaware County Bar attorneys | Reach attorneys not yet in roster | VP of Philanthropy
CLE #3 — Complex Assets & Succession | Late May 2027 | Breakfast CLE, 1.0 credit | PA roster + prospects (~75) | Position Foundation for S-corp, real estate, business-interest gifts | VP of Philanthropy + outside speaker
Summer recap & FY28 preview | June 2027 | Email + select calls | Active roster | Thank-you for referrals; preview FY28 programming | VP of Philanthropy
Standing advisor services (not calendared — always available):
• 24-hour technical response on client charitable planning questions.
• Joint client meetings on request; Foundation staff travel to advisor offices for high-stakes conversations.
• Third-party investment manager program — qualified advisors may continue managing fund assets [PLACEHOLDER — confirm Foundation program parameters].
• Advisor-specific portal access where appropriate; quarterly advisor eNewsletter distinct from donor eNewsletter.
• Sample bequest language, gift acceptance policy, and IRS documentation provided on request.

## Responsive Triggers
Responsive & Triggered Touchpoints
Stewardship that cannot be calendared because it responds to community events, donor life events, and fund activity.
Trigger | Response Timeline | Touchpoint | Audience | Channel | Owner
Rapid Response Fund activation (community emergency) | Within 48 hours of board authorization | Critical Needs Alert email + portal banner; matched giving window if applicable | All Tiers + community list | Email + portal + earned media | VP of Philanthropy + President + Communications
Major grant announced from donor's fund | Within 5 business days of approval | Personal note from VP of Philanthropy highlighting grantee impact; offer of grantee meeting | Tier 1–2 donors whose funds awarded the grant | Email/call + handwritten for Tier 1 | VP of Philanthropy
Fund anniversary (5, 10, 15, 20, 25 years) | On anniversary date | 5/10 yr = call; 15/20 yr = visit; 25+ yr = recognition feature [PLACEHOLDER format] | All applicable fundholders | Phone / in-person / publication | Assigned officer + Donor Services Manager
Donor life event (birth, marriage, graduation, retirement) | Within 10 days of awareness | Personal acknowledgment from CAO; no solicitation | Tier 1–3 | Handwritten card | Assigned officer + Donor Services Manager
Donor loss or hardship (death, illness, family loss) | Within 5 days of awareness | Condolence or care message from president; practical support if appropriate | All Tiers | Handwritten + phone | President + VP of Philanthropy
Successor advisor activation | At point of transition | Welcome conversation; review of donor history with FDC; tailored orientation | Successor advisor | In-person preferred | VP of Philanthropy
Anonymous gift from non-fundholder ≥ $5,000 | Within 5 business days | Personalized acknowledgment via mail with cultivation offer | Donor (with consent for further contact) | Mail + follow-up call if welcomed | VP of Philanthropy + President
First-time DAF grant from new fundholder | Within 5 business days of approval | Congratulatory note + offer to discuss grantmaking strategy | New fundholders in first 12 months | Email + scheduling outreach | Assigned officer
Press mention of donor or grantee | Within 5 business days | Share with donor; offer congratulations or condolences as appropriate | Tier 1–3 | Email + handwritten for Tier 1 | Communications flags; VP of Philanthropy acts
Lapsed donor signal (no gift/grant for 18 months) | At the 18-month mark | Outreach call to understand status; not a solicitation | All Tiers | Phone | Assigned officer

## Capacity
Capacity Model — FY27
Blue cells are inputs — replace with Foundation actuals.
Inputs — replace blue cells with FDC actuals
Total active fund holders | 565
Tier 1 — Philanthropic Advisory | 35 | Cap 30–40. Highest-touch relationships.
Tier 2 — Major Donor | 50 | Cap 75–100.
Tier 3 — Engaged Fundholder | 120 | Cap 100–125. Tier 2+3 combined ≈ 125-visit caseload.
Tier 4 — Standard Fundholder | 260 | Balance of portfolio.
Planned Gift / Legacy Society (overlay) | 50 | May overlap other tiers.
Professional Advisors (active roster) | 50 | Parallel track; cap 40–60.
FTE on donor services / philanthropy team | 3 | Includes fraction of CEO/president time on stewardship.
Available stewardship hours per FTE per year | 1000 | Assumes ~50% of FTE time on direct stewardship.
Average minutes per personal touch | 60 | Prep + the call/note + CRM logging. Tier 1 runs longer.
Touch frequencies by tier (per relationship, per year)
Tier 1 personal touches/year | 9 | Strategy sessions (fall + spring), summer touch-base, annual review, briefings, notes.
Tier 2 personal touches/year | 6 | Annual philanthropic review, mid-year check-in, year-end calls, asks.
Tier 3 personal touches/year | 4 | Annual fund report meeting + responsive support + narrative summaries.
Tier 4 personal touches/year | 1 | Statements drive most stewardship; ~1 personal touch.
Legacy overlay personal touches/year | 4 | Luncheon, year-end note, insider's-view briefing, anniversary/birthday.
Professional Advisor 1:1 touches/year | 3 | Excludes CLE attendance; F2F meetings & calls.
Calculations
Tier 1 personal touches | 315
Tier 2 personal touches | 300
Tier 3 personal touches | 480
Tier 4 personal touches | 260
Legacy overlay personal touches | 200
Professional Advisor personal touches | 150
TOTAL personal touches required per year | 1705
Time required vs. available
Total hours required per year for personal touches | 1705 | Total touches × minutes / 60.
Total stewardship hours available across team | 3000 | FTE × hours per FTE.
UTILIZATION (personal touches as % of stewardship hours) | 56.83% | Above 60% means the calendar is unrealistic at current staffing.
Implied visits per FTE (vs. 125 benchmark) | 365 | Tier 1–3 personal touches ÷ FTE.
Interpretation
Under 50% | Capacity is healthy. Consider deepening Tier 1 touches or expanding the Legacy Society program.
50–70% | Capacity is appropriate. Protect the calendar from getting heavier.
70–90% | Capacity is stretched. Reduce volume or narrow Tier 1–2 with stricter eligibility.
Over 90% | The calendar is unrealistic. Grow the team, narrow segments getting personal touches, or shift to templated outreach.